ACCESS DENIED

Senior Capstone Project for W.I.L.L.

The College of New Jersey

Spring 2004

Participants

Marni Bentley

Danielle Bertran

Nicole Calvano

Christine Mesropyan

Ariane Osit

Ashlee Stetser

Mary Kate Szenasy

Organizational Plan and Timeline

By: Ariane Osit

### Goal

To raise awareness about the trafficking of women worldwide, and to support a network of organizations dedicated to rehabilitating women who have been victimized.

#### Organizational Structure

Executive Chair- A person who is the Public Spokesperson, Coordinator, and Overseer of Committees

Three Committees-

- Publicity: Chairperson and webmaster

- Community Relations: Internal and External Relations

- Event Planning: Chairperson

#### Objectives

To conduct a Campus Awareness Campaign by:

-Having insightful information on trafficking in every building and residence halls

-Petition to the Office to Monitor and Combat the Trafficking in Persons

*Goal: 1400 signatures-200 per woman

-Have an event that is shocking, has lasting effects, and raises awareness/ initiative

#### Timeline

*Week 1- Week 2

-Join committees

-Gain understanding of issues and goals

-Generate ideas

-Create publicity material

-Brainstorm event ideas

*Week 3- Week 4

-Attain all necessary approvals

-Submit article to Signal

-Book Student Center table

-Book event location

-Get volunteers from different classes

*Week 5

-Launch Campus Awareness Campaign

-Hang all posters and banners, tabling in Student Center, Chalking

*Week 6

-EVENT

* Week 7- End of Semester

-Evaluate success of project

-Mail petition to the Office to Monitor and Combat Trafficking in Persons

#### Keep in Mind…

-Be realistic. Have a good idea of what you will be able to do.  It is better to do one thing well than many things at a mediocre level.

-Make sure everyone in the group has a good understanding of the issue and is contributing an equal part in the process.

Approvals and Materials

# By: Ashlee Stetser

Although this section may appear self-explanatory, it will provide the easiest way to obtain approvals and will outline suggestions for acquiring materials. Organization and foresight are the keys to making this component of the project successful!

#### Methodology

- Approvals

- Be sure all approvals are done in advance!

- Flyers and Table Tents

-Find the person in Campus Life (located on the second level of the Brower Student Center) who is responsible for stamping and signing the flyers.

-Usually, the will allocate two weeks for these to be displayed on campus, so have your dates in mind.

- Banner

-MUST BE DONE WELL IN ADVANCE in order to reserve a location for it to be hung in either the Brower Student Center, Travers/Wolfe or Eickhoff Hall for the dates that are needed.

-Be sure to have a sketch of the banner with you to present to the person in charge of banners in Campus Life.

- Location

-Decide where the event is to be held and reserve that as soon as possible.

*If outside, be sure to have a backup location planned.

-To reserve tables, chairs, an easel, and even a microphone: speak to Auxiliary Services and the Information Desk in the Brower Student Center.

- Materials

- Tax-exempt purchases

*Since you are students, you can apply for tax-exempt purchases and this will allow you to stretch out your budget, and in the end, save the organization money.

-Obtain a tax-exempt form in Campus Life.

-Bring this form to the place of purchase (i.e. Walmart, Target, etc.).

- Keep track of purchases

-Elect a very organized member of the group to be in charge of buying and responsible for the funds.

-To ensure reimbursement:

-Put your name and social security number on your receipts.

-Make copies of the receipts.

*If possible, it can be easier when one can have the money upfront!

- Here is a list of some materials we purchased for our project:

-tape

-paper (and lots of it!)

-poster board

-heavy duty marker

-10 yards of fabric

-a customized stamp (ACCESS DENIED)

-chalk

-paint

#### Keep in mind…

-Plan well in advance.

-Always prepare for the worst-case scenario. For example: have a rain date if needed and an alternate place in mind to hang a banner.

-Get approvals done early so this is out of the way and guaranteed.

-Think positively and be proud of what you are about to accomplish.

-OVER PLAN! Buy more materials than you estimate you’ll need, especially paper. All of this can be returned or used next year.

-Set high expectations! Even if you miss the moon, you will still land among the stars!

Publicity

By: Christine Mesropyan

Publicity is important because it serves as a tool to attract public interest.  Publicity is used to gain public attention or support.  Distributing of information to promote for an upcoming event is vital if you want people to be aware and feel inclined to support your event.  Publicity is particularly effective as it is a means to reach students on-campus as well as in the surrounding community.

Since so much of the success of ACCESS DENIED depended upon the surprise factor, publicity had to be approached in a rather untraditional way. In other words, we decided to use ‘teaser’ fliers and quarter sheets to promote our event.  Since we did not want to give out too much information regarding what we had planned for our demonstration, we had to find ways to advertise for the event while maintaining a level of secretiveness.  The reason for our decision to be sly was so that the campus would be shocked when they actually saw what we had planned.

We decided that in order to keep a consistency among our publicity all fliers, quarter sheets and fact sheets would be printed on red paper and stamped “ACCESS DENIED.”  Although the primary information on the fliers was limited to the date, time, and location of the event, we were aware that they express somehow that the event was focused on the trafficking of women. A lot of time was put into brainstorming and coming up with how we wanted to go about advertising.  Some concerns that were raised included:

- Being cautious of how individuals may perceive fliers that discussed how trafficking is considered slavery.

- Trying to keep the information as simple as possible, but still getting enough out.

- Figuring out what facts would be the most effective.

Once we were able to work out those concerns, we got rolling with publicity.

Methodology

- Prepared the fliers and quarter sheets (see attached drafts).

- Got them approved for posting.

- Decided where to post the fliers on campus.

- Made appropriate number of copies.

- Divided the fliers and posted them in designated spots.

- Placed an advertisement in the Signal a week before the date of the event.

- MaryLynn was able to get Lisa Myers to come to our class and speak with us.  We gave her information about our event and she sent out release to news stations and radio stations.

- MaryLynn also made sure that the Signal was covering our event.

- The day before the event we set up shifts to give out quarter sheets to people in front of the Brower Student Center and we also placed them on tables in the Brower Student Center and in some Academic Buildings.

- The fact sheets were used the day of the demonstration.

  - They were given to individuals who volunteered to help us with the event so that they could learn more about Trafficking of Women.

  - They were also given to individuals who signed the petition to combat Trafficking of Persons.

- The day of the event there was a great deal of media taking pictures and interviewing individuals. This was great because it would help to spread the information beyond the college campus community.

- In order to produce the table tents as part of the post-event awareness campaign, we used the same fact sheets and got them approved again. We met as a group in order to fold and staple the table tents.

- We placed these table tents on tables in Eickoff Hall, Travers/Wolfe Cafeteria, and the Brower Student Center Food Court.

Keep in Mind…

-It is absolutely necessary to make sure to be aware of your deadlines so that the fliers and quarter sheets will be hung/distributed during the most effective times to promote the event.

-Be sure to get approvals for everything and to keep up with the Timeline that your group has arranged.

Did you know…

700, 000-

2 MILLION

WOMEN…

Are trafficked (ANNUALLY)!

TRAFFICKING of WOMEN…

If you thought SLAVERY was a thing of the past,

You’ve made a BIG,

Better yet,

HUGE,

MISTAKE!

SHOCKING FACT:

The United States is the second highest destination country to where women are trafficked.**

** Mizus, Marisa and Maryam Moody, Cindy Privado, Carol Anne Douglas et al. "Germany, U.S. Receive Most Sex-Trafficked Women."  Off Our Backs.  Jul/Aug 2003.  Proquest.  February 2004.

Ad for the Signal (Modified)

ACCESS  DENIED                                                                                                                                  TRAFFICK!

Trafficking of Women Fact Sheet

- Between 700,000 - 2 million women are trafficked across national borders annually

- Trafficking occurs in North America, South America, Europe, Asia, Africa, and Australia; the United States is the 2nd most frequent destination of trafficked women, Germany being number 1

- Traffickers earn between $250 - $25,000 per shipment-it’s a billion dollar business as profitable as the drug trade, but increasing in popularity because the penalties are so slight

- Most women are trafficked for the purpose of prostitution-their travel documents are stolen by their pimps or traffickers, and they are forced into debt bondage in which they must repay their purchase price, travel and any other expenses incurred

- These women are recruited through media advertisements offering high paying jobs in foreign countries for being a waitress, nanny, or dancer, through mail-order-bride agencies, and through female recruiters acting as trusting friends who recommend overseas jobs

- Trafficking networks are modern day slave traders-there are sometimes even auctions-extreme violence is used to control the women, including beatings, burnings, and rape…women are even murdered as punishment when they refuse to engage in prostitution

- Causes of trafficking include: poverty, unemployment, inflation, war, and a lack of a promising future

- The U.N. first acknowledged the existence of trafficking of women in 1949…more than 50 years ago, yet still minimal legislation exists...with so many corrupt officials, police, and other law enforcers, NGOs have taken the lead in anti-trafficking efforts

- The United States’ government currently dominates the global anti-trafficking movement through their annual Trafficking in Persons Report….

PLEASE HELP US TO PUT PRESSURE ON THE U.S. GOVERNMENT TO ENFORCE STRICTER ANTI-TRAFFICKING POLICIES AROUND THE WORLD BY SIGNING THE PETITION

*SOURCES: Tzvetkova, Marina. “’NGO responses to trafficking in women’: Gender and Development” Vol. 10, No.1, March 2002: 60-68.  Wallace, Melanie R. “’Voiceless Victims: Sex Slavery and Trafficking of African Women in Western Europe’: The Georgia Journal of International and Comparative Law”, Spring 2002: web.lexis-nexis.com/universe/document?_m=e64361d8b95de00116c7fca343e6eb35.

Hughes, Donna. “’The ‘Natasha’ Trade: The Transnational shadow market of trafficking in women’: Journal of International Affairs”, Vol. 53, Issue 2, Spring 2000.  “US Department of State Trafficking Persons Report”: United States Department of State. Trafficking of persons report: 2003. Washington, DC: GPO, 2003.

Recruiting Volunteers

By: Marni Bentley

Once our group “Access Denied” had things underway, one crucial element that began to arise was that of attracting and organizing volunteers.

The trafficking of women is a difficult topic to spread awareness for, especially to the students and population at our school.  Because "Access Denied" came to this realization early in the designing process of this grass roots organization, we concluded that a truly shocking event would create the effect and impact desired for this project.  This is when we knew that the more people we had involved in this presentation, the bigger impression it would leave on the public.  At this point we decided to contact teachers in the Women's and Genders Department, thinking we would get a positive response from people who may be more educated about this human rights issue.  We knew that getting the numbers of volunteers we hoped for (approximately one hundred females) was dependent upon the support and involvement of these professors.

##### Methodology

- Email the W.I.L.L. Listserve in order to ask for volunteers.

- Obtain the Women's and Gender Studies list of teachers and the schedule of when they teach class.

- Divide and Conquer.

- Display the teachers’ names and when they teach.

- Group members will choose which classes they will attend in order to eagerly recruit the volunteers.

- Before going to the class:

- Email a letter to the teachers. This should explain the project in little detail, and ask permission to come to their class to preach about the project. Be sure to find out when is the best time to come (i.e. the beginning or end of class).

- The letter sent to the teachers should also include some ideas on how to bribe their students in order for them to want to volunteer.  People are more willing to help if they see some kind of immediate benefit.

- We enticed the volunteers for our project by telling the teachers to possibly implement this project as extra credit or offer this project in place of a class or an assignment.

- Do not spoil the shock effect!

- In order to get volunteers, you must be enthusiastic in sharing with them the reason for and importance of their involvement.

- For this project, we told the volunteers that the dates and commitment were going to be enforced and once they signed up, they could not back down. We did not tell the volunteers what they were doing until the day they showed up to help.

- For volunteers that could not meet on the day or time, or that are male:

- We provided other options for these people, so they could obtain extra credit and still help us with the project.

- These people who also wanted to help were assigned to chalking, handing out quarter sheets and helping to post flyers throughout campus.

- Compile the contact information.

- When speaking to each class, have each volunteer sign up by including their name, email, extension, and the name of their professors.

- Create an excel spreadsheet of this information.

- A contact email was made available for those with further questions about the project.

- The compilation of names and information was sent to the designated recruiter member of the group, who then put the list together into one.

- Email the volunteers frequently.

- The emails were separate for the women who were volunteering the day of versus the volunteers who could help at other specified times.

- All emails should be written with enthusiasm and include the specific times and locations to meet.

- The women who volunteered for the day of the demonstration were notified a week before the event that it would take place rain or shine!

- Assign someone to be in charge of the volunteer list on the day of the event.

- Formulate an attendance sheet for this person to use so that all students are given credit.

- On the actual day of the activism project, the member in charge of the main list of volunteers checked people in and wrote down which teachers they were there for.

###### Keep in Mind…

-This may not seem like a huge undertaking as far as positions are concerned for this project, but do not be fooled.  Getting the volunteers and keeping in contact with them is very important for the outcome of the final demonstration.

-Be careful not to divide the major list of volunteers and also send a fact sheet to the volunteers in the last email sent to the female demonstrators so they know some facts about the topic they are "standing" for.

-It is also important to send a thank you email to the professors for their support.

Initial Email to the W.I.L.L. Listserve (or any other organization’s list)

Dear Wonderful Women of W.I.L.L.

Do you know that the United States is the second largest host country to the importation of women? Did you know that this happens to 700,000-2,000,000 women each year and this industry profits over $6,000,000,000? Stop the slavery. PLEASE HELP US!

We, the women of the Senior Capstone Class, are asking for your support. Over the past semester, Mary Lynn W. Hopps and our class of seven females have decided upon an activism project against the trafficking of women, and we need your organization’s help in order for this event to be successful. We are in the process of creating an event that will promote shocking statistics and images throughout the campus.

The goal of this project launch is to educate and enhance student awareness about this transnational human rights issue. We are anticipating the project launch to take place on Tuesday, April 13th, at noon. WE NEED YOUR HELP! We are trying to keep this project somewhat of a secret as to amplify the shock effect on our campus. We would like to have as many women as possible to help us with the demonstration and we hope to have men help gain signatures for the petitions and help chalk as well. This is a great opportunity to gain awareness on an important topic that will blow your mind.

Thank you for your time, and please email bentley2@tcnj.edu or stetser2@tcnj.edu with your name and email to participate.

And remember, it won’t be long before you are all taking this class, so PLEASE help us, and do your part as a feminist and member of W.I.L.L. to spread awareness about this horrifying issue!

Sincerely,

Marni, Ashlee, Danielle, Mary Kate, Nicole, Christine, Ariane

Initial Email to the Professors

Dear Valued Professors,

We, the women of the Senior Capstone W.I.L.L. class, are asking for your support. Over the past semester, Mary Lynn W. Hopps and our class of seven females have decided upon an activism project against the trafficking of women, and we need your students’ help in order for this event to be successful. We are in the process of creating an event that will promote shocking statistics and images throughout the campus. The goal of this project launch is to educate and enhance student awareness about this transnational feminist issue. We are asking your permission to come into your classrooms to gain participants for our project. We prefer women to partake in the actual demonstration, and the men will help to encourage petition signing, chalking and handing out pamphlets. We are anticipating the project launch to take place on Tuesday, April 13th, at noon.

To encourage the students in your classes to participate we know there needs to be some type of incentive. We hope that you can incorporate this grassroots movement into your syllabus and will reward the students with either extra credit, or in lieu of a class, so that we may get as many people as possible. We will keep track of the participants and will report their names back to you on April 13th, at the end of the day.

Again, we are asking for five minutes before class to have a representative speak briefly about our cause, and we will provide a sign up sheet. We are trying to keep this project somewhat of a secret as to amplify the shock effect on our campus. Please email me and let me know if I can attend your 2:00 class tomorrow to speak briefly on the issue. I would also need to know where your class is held so that I can make an appearance.

Thank you for your time and assistance.

Sincerely,

Marni, Ashlee, Danielle, Mary Kate, Nicole, Christine, Ariane

Thank You Email sent to the Professors

Dear Valued Professors,

On behalf of the W.I.L.L. Capstone Class, I would like to thank you for your classtime and support. We greatly appreciate your willingness to participate and help our cause against the trafficking of women. Hopefully with the help of your students this activism project will be a great success!

Thanks again!

Marni, Ashlee, Danielle, Mary Kate, Nicole, Christine, Ariane

Trafficking Stories

By: Mary Kate Szenasy

Although the trafficking of women is a truly global problem, not many individuals in the campus or local community can say that they personally know a trafficking victim.  This makes the problem of creating interest in and empathy for the issue problematic, since most people cannot relate to it.  Disclosing the personal stories of trafficked women was our attempt to bring the campus and local community closer to the victims and in turn, provide a catalyst for action.

Methodology

- Research Stories of Trafficking Victims

  - Internet Search Engines such as Google.com are a good place to start.  Search “trafficking and personal stories,” for example.

  - NGOs advocating for trafficking victims often have access to the stories of trafficked women.

  - Usaid.com and Christianaid.com were the source of many of the trafficking stories we used.

- Seek out a sample of stories that represent women from various source and destination countries.

  - Trafficking occurs on every continent in the world except Antarctica.  The range of stories used should reflect the global nature of trafficking.

  - The United States is the second largest destination country for trafficked women.  Using the stories of women trafficked to the United States is important for the public to recognize that the trafficking occurs right in our own backyards.

- Break down stories into a few powerful lines.

  - The longer the story, the less likely individuals will take the time to read it.

  - Include the victim’s name and age, if possible, to make the story more personal.

  - Include the source and destination country in the story to enhance understanding of global trafficking.

- Use the stories as part of the consciousness-raising campaign.

  - For our purposes, the stories were transposed onto large posters to be held by women during the demonstration.

  - Personal stories of trafficking victims can be used in various ways, including informational brochures, press releases, or editorials.

Keep in Mind…

-The level of awareness of your audience.

- There is a very low level of awareness about the issue of trafficking, so the stories represented a first glimpse at the issue for many individuals.  With this in mind, we did not want to use stories that would make the trafficking issue unclear.  We also sought to use stories that include some of the most common ways women are trafficked.

- As the level of awareness of trafficking increases, stories should become more diversified and representative of the complex nature of the problem.

-Some stories might lead individuals to confuse trafficking with a related, but different issue.

- While trafficking is a form of prostitution, an integral component of trafficking is forced prostitution. Stories that do not relay this idea should not be used.

Petition

## By: Mary Kate Szenasy

Although our primary goal for this year’s activism project was to raise awareness in the campus community about trafficking, we wanted to be sure that our efforts would be translated into some kind of action.  In the early stages of awareness about the problem and with limited understanding of the complexity of trafficking, we thought it unlikely that individuals would donate money that could be sent to NGOs in other countries to rehabilitate victims.  We did think, however, that individuals would be willing to sign a petition to send to a government institution in response to the problem.

Methodology

- Research government institutions, NGOs, or other organizations that play or might play a leading or influential role in the movement against the trafficking of persons.

- Overview of the Office to Monitor and Combat Trafficking in Persons and the Office’s Annual Trafficking in Persons Report (U.S. Department of State Online):

The annual Trafficking in Persons Report (TIP Report) is the most comprehensive worldwide report on the efforts of governments to combat severe forms of trafficking in persons. The State Department issues the report to Congress as required by the Trafficking Victims Protection Act (Division A of Public Law 106-386). The law was enacted in October 2000 to combat human trafficking by ensuring the effective punishment of traffickers, enhancing protection for victims, and creating significant mandates for the Departments of State, Justice, Labor, Health and Human Services and the U.S. Agency for International Development. The Department of Justice expects to issue a progress report on the U.S. Government’s domestic anti-trafficking efforts later this year.

The annual trafficking report includes those countries determined to have a significant number of victims of severe forms of trafficking. The narratives provide an overview of the trafficking situation in the country and the government’s efforts to combat trafficking. The first paragraph of each narrative describes the scope and nature of the trafficking problem in the country, and thus indicates the reasons the country has been included in the report. The second paragraph indicates the extent of the government’s compliance with minimum standards and includes some suggestions for efforts to combat trafficking. The succeeding paragraphs describe some of the government’s efforts to prevent trafficking, prosecute traffickers, and protect victims, and thus illustrate the reasons the country has been placed in Tier 1, 2 or 3 of the report. The narratives do not include extensive details, comprehensive information about the countries or their governments, or the extent of anti-trafficking activities undertaken by non-governmental entities.

Establishing task forces and action plans are methods that some countries have successfully used to create goals and benchmarks for their anti-trafficking efforts. However, these plans and task forces, on their own, are not weighted heavily in assessing country placements. Rather, the report focuses on concrete efforts that governments have undertaken to combat trafficking. Similarly, the report does not weigh heavily laws that are in draft form or that have not been enacted, because they cannot yet be used to combat trafficking. In some cases, task forces, action plans or draft laws have been mentioned in a country narrative as examples of a positive attitude, or preliminary steps that the government is beginning to take to combat trafficking.

Last year (2003), for the first time, governments that were not making significant efforts to bring themselves into compliance with the minimum standards-those listed on Tier 3-faced potential sanctions that included loss of certain types of U.S. assistance; such sanctions would be subject to possible waiver. In this year’s report, several countries have moved from their placement in last year’s report. Thirty countries are included for the first time in the TIP report due to increased information on the scope and magnitude of trafficking.

This report is a diplomatic tool for the U.S. Government as an instrument for continued dialogue, encouragement for the current work of some governments, and a guide to help focus resources on prosecution, protection, and prevention programs and policies. After the release of this year’s TIP Report, as in past years, the Department will continue to engage governments about the content of the report to help strengthen cooperative efforts to eradicate trafficking. In the next year, and particularly in the months before a determination is made regarding sanctions for Tier 3 countries, the Department will use the information gained in the compilation of this year’s report to target assistance programs more effectively and to work with countries that need help in combating trafficking. Finally, the Department hopes the report will be a catalyst for government and non-government efforts to combat trafficking in persons around the world.

- Research if any petitions are currently underway or independently decide what issues are most important to include in the petition.

- We found a petition already underway for the Office to Monitor and Combat Trafficking in Persons.  (See Petition on Separate Paper)

- Formulate the petition.

- Be sure to have a place for individuals to print their name, address, and signature.

- Be sure that the petition is formatted appropriately.  Find an example of a petition to use as a guide.

- Decide how signatures will be collected; i.e.: when and where.

- We primarily collected signatures for the petition during the demonstration, because it was during this time that the issue was most salient in the minds of those present.

- Members of our class also collected signatures independently in the days and weeks following the event.

- Set a goal for the number of signatures you would like to obtain.

- Your goal should be realistic and attainable.

- Our goal was to collect 1400 signatures.  This was derived from the number of people in our class (200 signatures for each of the 7 students).

- If you do not get the number of signatures you anticipated, consider extending the collection period.

- Provide supporting information so individuals know what they are signing and understand the issue.

- We had fact sheets on hand with information about trafficking to be distributed to any individual who signed the petition.

- Every individual who collected signatures was thoroughly briefed on trafficking so as to be able to answer any questions that might arise.

- Send the Petition to the party you chose upon completion.

Keep in Mind…

-When and where individuals are most likely to respond

- Approaching individuals while they are eating, for example, might annoy them.

- Many people delete emails before they even read them, indicating that sending the petition through email might not be the most effective method.

TO: The Office to Monitor and Combat Trafficking in Persons

WHEREAS all individuals have the right to be protected from trafficking and forced prostitution

WE, the undersigned, petition the Office to Monitor and Combat Trafficking in Persons as follows:

Evaluate anti-trafficking measures: The Trafficking Report should evaluate the content and effectiveness of each country’s actions to fight trafficking.

Include statistics: In order to understand the scope and nature of trafficking, disaggregated data on victims and prosecutions should be provided, which governments should be urged to compile.

Be more precise:  The 2004 Trafficking Report should be more specific about: the content of the trafficking legislation in each country; state complicity; investigations and prosecutions of traffickers; accessibility and effectiveness of witness protection and victim services programs; and whether the country is a party to the U.N. Trafficking Protocol.

Explain Tier movement: The 2004 Trafficking Report should say why some countries moved from one Tier to another.

| Name (printed) | Address (printed) | Signature |
| --- | --- | --- |

Reflection: Overall Success of Project

Number of Participants

- Approximately 50 women

Number of Signatures

- Goal: 1400

- From the Event: Approximately 400

Awareness

- Posted flyers prior to the event

- Handed out fact sheets at the event

- People read stories of trafficked women at the event

- Table tents during the weeks following the event

- All publicity, i.e. Signal article, Trenton Times article, etc.

Publicity

- Article in the Trenton Times

- Received air time on Channel 6 News

- Article in the Signal

- Picture and caption in the NY Times

Event Follow-Up

- Thank you cards to professors and students who helped

- Post-awareness campaign

Overall Impact of the Event

- Petition

- Raised awareness

- Designed and implemented a grassroots organization on campus

Suggestions for the Future

- With more students in the class, it will be important to establish an organizational structure, i.e. an executive chair, committees and committee chairs

- It would be more productive to choose a topic earlier in the semester so that there is more time to work on the final activist project to make it bigger and better!

- Now that we have used the element of “shock-value” for our event, you will need to come up with another way to get this apathetic campus’s attention!

- If you continue to work on the issue of trafficking, a possible goal for the future is to establish safe houses in the area since there are none in the United States.

- Another possible goal for next year is to raise money in some way (a charity run, a benefit concert, etc.) to combat trafficking

- The creation of a documentary on the issue might also help to spread awareness and could be shown in different classes.

# Text boxes

TUESDAY:

April 13, 2004 @ 12PM

Outside the Student Center

TUESDAY:

April 13, 2004 @ 12PM

Outside the Student Center

NOT

FOR SALE!

TUESDAY

APRIL 13TH, 2004 @ 12 PM

Outside the Student Center

TUESDAY:

April 13TH   @ 12PM

Outside the Student Center

TUESDAY:

April 13, 2004 @ 12PM

Outside the Student Center